## Sheet1
Task | Subtask
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | 1/17-1/24 | 1/25-1/31 | 2/1 - 2/7 | 2/8 - 2/14 | 2/15 - 2/21 | 2/22 - 2/28 | 3/1 - 3/7
Reconsider firebase realtime database vs firebase firestore | bar: 1 to 2
| Identify pros | 1: completed
| Identify cons | 1: completed
Preliminary drawing of datastorage | bar: 1 to 2
Redesign database (regardless of realtime or firestore) | bar: 2
Should include plant species as specific to row/column location | bar: 2
Read from firebase firestore database | bar: 2
Redesign selection path (to account for an understanding of tasks as connected to plant species vs field site) | bar: 2 to 4
Change screen order | bar: 3 to 5
Redesign the way plants are loaded onto the plant selection screen | bar: 2 to 4
Each button should contain information about its associated plant (at a given row and column index location) --> dynamically loaded | bar: 2 to 4
Two options: Either load grid by row/column. Or, load each button by plant numbers. | bar: 2 to 4
Learn how to prefill Google forms |  | 1: completed
Prefill a Google Forms using data from the app (for example, a task form prefilled with field site, block, and plant location) | bar: 4 to 6
Learn: is it possible for firebase to read from a Google Sheets? | bar: 5
If it is possible, prefill an EXAMPLE database with an EXAMPLE sheets. | bar: 5 to 7
Replace hard coded picker lists with the data read from the database | bar: 5 to 7
Replace hard coded link following (to survey) with data from the database | bar: 5 to 7
Julia
Hamad
Alex
Julia & Hamad
Hamad & Alex
Julia & Alex
Julia & Hamad & Alex